## Jun-Aug(2023)
Name: Alex Fernan F. Mercado | [6 empty] | Project Gantt Chart (2023) | [6 empty] | Legend:
Project: | PR & PO Approval/Disapproval Email Notification , Accounting Module - Daily P&L (Pivot Report) | [13 empty] | Estimated
DRF #: | [14 empty] | Actual
Activity | JUNE |  |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  |  | NOVEMBER
| W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
Creating approval & disapproval function in email | JUNE W2: 2023-06-06
2023-06-06
PR: Creating redirect link to odoo pr form & odoo aproval dashboard in email | JUNE W2: 2023-06-07
2023-06-07
Automatic sending of email once PR is disapproved | JUNE W2: 2023-06-08
2023-06-08
PR: Fix: Multiple approvers not showing base on department | JUNE W2: 2023-06-09
2023-06-09
Automatic sending of approved PR to next Approver’s email | JUNE W3: 2023-06-13
2023-06-13
Automatic sending of email once PR is approved by final approver | JUNE W3: 2023-06-14
2023-06-14
Creating of PO Email Template | JUNE W3: 2023-06-15
2023-06-15
PO: Creating approval & disapproval function in email | JUNE W3: 2023-06-16
Creating redirect link to odoo PO form & odoo aproval dashboard in email | JUNE W4: 2023-06-19
2023-06-19
Creating Pop-up window When Disapproved button is clicked in email | JUNE W4: 2023-06-20
2023-06-20
PO: Automatic sending of email once PO is disapproved | JUNE W4: 2023-06-21
2023-06-21
PO: Automatic sending of approved PO will to next Approver’s email | JUNE W4: 2023-06-22
2023-06-22
PO: Automatic sending of email once PR is approved by final approver | JUNE W4: 2023-06-23
2023-06-23
Upload Approval Module to OdooDev | JUNE W5: 2023-06-26
2023-06-27
Testing of Approval Module | JUNE W5: 2023-06-27
2023-06-28
Accounting Module - Daily P&L (Pivot Report) Adding new field for P&L ID | JUNE W5: 2023-06-28
2023-06-28
Adding filters per Month | JUNE W5: 2023-06-29
2023-06-29
Adding filters per Quarterly | JUNE W5: 2023-06-30
2023-06-29
Adding filters per Analytic Accounts | JULY W1: 2023-07-04
2023-07-04
Odoo PR-PO Presentation | JULY W1: 2023-07-05
2023-07-05
Testing of Accounting Module - Daily P&L (Pivot Report) | JULY W1: 2023-07-06
2023-07-06
Query For Balance Sheet | JULY W1: 2023-07-07
2023-07-07
Implement auto-email functionality for new PR approver | JULY W2: 2023-07-10
2023-07-10
Implement auto-email functionality for new PO approver, Fix email links | JULY W2: 2023-07-11
2023-07-11
Token generation function for new approver | JULY W2: 2023-07-12
2023-07-12
Sending of email notification to Purchase Representative | JULY W2: 2023-07-13; AUGUST W1: ``
2023-07-13
Update approval module in OdooDev | JULY W2: 2023-07-14
2023-07-14
Make forms readonly once approved or disapproved | JULY W3: 2023-07-17
2023-07-17
Refactor Approval Module with added features into Separate Moduel | JULY W3: 2023-07-18
2023-07-18
Additional Features for Purchase Order | JULY W3: 2023-07-19
2023-07-19
Fix purchase agreement not showing, Refactor code in views | JULY W3: 2023-07-20
2023-07-20
Upload/Testing approval module extension in OdooDev | JULY W3: 2023-07-21
2023-07-21
Displaying Pivot View and Query for Balance Sheet | JULY W4: 2023-07-24
2023-07-24
Query For Profit and Loss | JULY W4: 2023-07-25
2023-07-25
Query For Balance Sheet: Total Current Assets, Total Non-current Assets, Total Assets, Total Current Liabilities | JULY W4: 2023-07-26
2023-07-26
Query For Balance Sheet: TOTAL NON-CURRENT LIABILITIES, TOTAL LIABILITIES, TOTAL CAPITAL DEFICIENCY | JULY W4: 2023-07-27
2023-07-27
Display filtered Tables in Pivot View | JULY W4: 2023-07-28
2023-07-28
Create separate Page for PNL with Total COGS and Gross Profit | JULY W5: 2023-07-31
2023-07-31
Add nav-tabs, yearpicker filter, display table total income loss | AUGUST W1: 2023-08-01
2023-08-01
Add Template Header, Include category name with chart of accounts | AUGUST W1: 2023-08-02
2023-08-02
Refactor Approval Module with added features into Separate Moduel | AUGUST W1: 2023-08-03
2023-08-03
Generation of report in BS & PNL, Export file rename when downloading | AUGUST W1: 2023-08-04
2023-08-04
Initial UI Design using PySide6. | AUGUST W2: 2023-08-07
2023-08-07
Implement the GUI based on the design. | AUGUST W2: 2023-08-08
2023-08-08
Add Functionalities. | AUGUST W2: 2023-08-09
2023-08-09
Create function to fetched data from matrix.json, Display data in table, Add logout messagebox | AUGUST W2: 2023-08-10
2023-08-10
Add function to prioritize MO, Filter PPC employees, Create UI for MO details | AUGUST W2: 2023-08-11
2023-08-11
Create UI for MO details, Display MO details when first row is clicked | AUGUST W3: 2023-08-14
2023-08-14
CREATE UI for Request Ticket. Display Machine, Datetime and Requestor | AUGUST W3: 2023-08-15
2023-08-15
Operator Ticket Request - Add function to send ticket to CMMS, Validation for ticket base on DTNO, | AUGUST W3: 2023-08-16
2023-08-16
MO details - Add START and STOP Button, Add password validation before completing an MO, | AUGUST W3: 2023-08-17
2023-08-17
Add function to record user activity logs, Display logs in main dashboard. | AUGUST W3: 2023-08-18
2023-08-18
Fix activity_log path, Add function to display only the last 5 activities of user.Redirect to main window when operator logout. | AUGUST W4: 2023-08-22
2023-08-22
Add more info of MO, Fix START, STOP states, Redesign MO details GUI | AUGUST W4: 2023-08-23
2023-08-23
Display remaining mo qty, Add function to calculate remaining MO qty. | AUGUST W4: 2023-08-24
2023-08-24
ADD operator machine status with validation. Add function to moved completed MO to bottom. | AUGUST W4: 2023-08-25
2023-08-25
Instead of disabling start/stop btn change it to hide. Add refresh button for table. | AUGUST W5: 2023-08-29
2023-08-29
Fix not saving to mo_logs. when there is no data Allow to only display one main window of MO details. | AUGUST W5: 2023-08-30
2023-08-30
Add function to move MO down when completed. Display current MO status. | AUGUST W5: 2023-08-31
2023-08-31

## IOT
Project Title | Activity | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER
|  | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
IoT | Initial UI Design using PySide6. | bar: AUGUST W2
2023-08-07
Implement the GUI based on the design. | bar: AUGUST W2
2023-08-08
Add Functionalities. | bar: AUGUST W2
2023-08-09
Create function to fetched data from matrix.json, Display data in table, Add logout messagebox | bar: AUGUST W2
2023-08-10
Add function to prioritize MO, Filter PPC employees, Create UI for MO details | bar: AUGUST W2
2023-08-11
Create UI for MO details, Display MO details when first row is clicked | bar: AUGUST W3
2023-08-14
CREATE UI for Request Ticket. Display Machine, Datetime and Requestor | bar: AUGUST W3
2023-08-15
Operator Ticket Request - Add function to send ticket to CMMS, Validation for ticket base on DTNO, | bar: AUGUST W3
2023-08-16
MO details - Add START and STOP Button, Add password validation before completing an MO, | bar: AUGUST W3
2023-08-17
Add function to record user activity logs, Display logs in main dashboard. | bar: AUGUST W3
2023-08-18
Fix activity_log path, Add function to display only the last 5 activities of user.Redirect to main window when operator logout. | bar: AUGUST W4
2023-08-22
Add more info of MO, Fix START, STOP states, Redesign MO details GUI | bar: AUGUST W4
2023-08-23
Display remaining mo qty, Add function to calculate remaining MO qty. | bar: AUGUST W4
2023-08-24
ADD operator machine status with validation. Add function to moved completed MO to bottom. | bar: AUGUST W4
2023-08-25
Instead of disabling start/stop btn change it to hide. Add refresh button for table. | bar: AUGUST W5
2023-08-29
Fix not saving to mo_logs. when there is no data Allow to only display one main window of MO details. | bar: AUGUST W5
2023-08-30
Add function to move MO down when completed. Display current MO status. | bar: AUGUST W5
2023-08-31
Remove refresh btn instead automatically move MO down when status Change. MEETING | bar: SEPTEMBER W1
2023-09-01
Designing To Figma with correct resolution. | bar: SEPTEMBER W2
2023-09-05
Implementing functions to new GUI | bar: SEPTEMBER W2
2023-09-08
Test system resolution in small monitor. | bar: SEPTEMBER W2
2023-09-08
Adjust font size, and UI issue. Make logs entry text bigger | bar: SEPTEMBER W3
2023-09-11
Fix user logs not updating in main dashboard | bar: SEPTEMBER W3
2023-09-12
Add MO Status Column | bar: SEPTEMBER W3
2023-09-13
Automatic moving of MO base on status | bar: SEPTEMBER W3
2023-09-13
Fix remaining MO qty not showing at start | bar: SEPTEMBER W3
2023-09-14
Fix multiple entry on downtime | bar: SEPTEMBER W3
2023-09-14
Change OEE formula calculation | bar: SEPTEMBER W3
2023-09-15
Create function to turn Light Tower on | bar: SEPTEMBER W4
2023-09-18
Add trigger for Downtime, Idle, and Start. | bar: SEPTEMBER W4
2023-09-19
Connect Button for machine ON and OFF.Add function to capture button inputs | bar: SEPTEMBER W4
2023-09-20
Fix window not getting destroyed. Remove clock in main dashboard | bar: SEPTEMBER W4
2023-09-21
Add heatsink to Raspberry pi. Add Refresh graphs button | bar: SEPTEMBER W4
2023-09-22
Implement RFID for logging in. Implement RFID to MO Swapping | bar: SEPTEMBER W5
2023-09-25
RFID authentication for stopping MO | bar: SEPTEMBER W5
2023-09-26
Optimize graphs and label update function | bar: SEPTEMBER W5
2023-09-27
Allow to only display one ticket and MO details window. Passing All data transaction to server | bar: SEPTEMBER W5
2023-09-28
Add function to only allow operator who started the MO to scan his/her RFID. Hardware setup. | bar: SEPTEMBER W5
2023-09-29
Assisting Maintenance Partner to setup IOT's in wirebond | bar: OCTOBER W1
2023-10-04
Actual Testing | bar: OCTOBER W1
2023-10-05
Prepared by: | John Raymark Llavanes
MIS Developer
Acknowledge by: | Emmanuel Natividad
MIS Manager